## Communication plan
COMMUNICATION PLAN
Communication Description | Communication Schedule | Initiated By | Recipients | Mode of Communication
Status Report to client | Weekly | Consultant | Client/Senior management | E-Mail
Management Review | Adhoc | ITPMO | Semior Management, Project Team | E Mail
Configuration Audit | At the end of each release | Consultant/Project Manager | Team Member | E mail
Project status report | Adhoc | Consultant/Project Manager | Team members | E Mail
External Escalation
Escalation level | Name | Role | Mail-ID | Phone-Number
Level 1 | Project Manager | Project Manager | To be provided | To be provided
Level 2 | Client | Project Owner/ Technical Lead | To be provided | To be provided
Level 3 | Project Sponsor | Project Sponsor | To be provided | To be provided

## Raci Matrix
Responsible | R
Accountable | A
Consulted | C
Informed | I
RACI MATRIX
Task | Consultant | Project Manager | Project Owner | Project Sponsor | IT Department | Operations Team/Employee
Status Update | R. A | R | I | I | I | I
Requirement gathering (Current state analysis, proposed state analysis, Risk, assumptions, constraints, and functional requirements) | R | I | A | C | C | C
Documentation | R, A
SECURITY ASSESSMENT | I | A | I | I | C
Documentation Sign-off | I | A | C | C | C | I
SOLUTION DEVELOPMENT | C | I | I | I | A | I
USER REVIEW | A | R, I | R, A, C, I | C. I | R, A, C, I | R, C, I
SYSTEM INTEGRATION TESTING | R, A, C | I | I | I | R, A, C | I
Vulnerability Assessment | I | I | I | I | R, A, C
User Acceptance Testing (UAT) | R, A | I | R, A, C, I | R, A, C, I | R, A, C | R, A, C, I
UAT SIGN-OFF | I | A | R | R | R | R
Database Access Request | I | R. A | I | I | C. I
Change Control Board Approval | C | R | R, A | I | I | I
DEPLOYMENT (Pilot) | C | I | I | I | R, A | I
Go-live Approvals | I | A | R | R | I | I
DEPLOYMENT (G0-live) | C, I | I | I | I | R, A | I
Training | R, A, C | I | I | I | I | I