## Project Plan
PROJECT NAME |  | STATUS |  |  | % DONE |  | START DATE | DUE DATE | PROPOSED DURATION (Days) | EXPECTED COMPLETION DATE
|  | On Track |  |  | 19.83% |  | 2024-12-20 | 2025-04-17 | 100 | 2025-04-30
Description: This proposed solution involves the optimization and automation of the reconciliation and settlement processes for my client.
MILESTONES | RESPONSIBILITY | STATUS |  |  | % DONE | Weighted | START DATE | DUE DATE |  |  | STATUS KEY
Requirement gathering (Current state analysis, proposed state analysis, Risk, assumptions, constraints, and functional requirements) | BUSINESS ANALYST | Completed | 9 | 0.15517 | 100% | 15.52% | 2024-12-20 | 2025-01-07 |  |  | On Track
Documentation | BUSINESS ANALYST | On Track | 5 | 0.086207 | 50% | 4.31% | 2025-01-07 | 2025-01-10 |  |  | Completed
SECURITY ASSESSMENT | INFOSEC | Not Started | 5 | 0.086207 | 0% | 0% | 2025-01-10 | 2025-01-12 |  |  | Not Started
Documentation Sign-off | NECESSARY STAKEHOLDERS | Not Started |  |  | 0% | 0% | 2025-01-13 | 2025-01-16
SOLUTION DEVELOPMENT | DEVELOPER | Not Started | 20 | 0.34483 | 0% | 0% | 2025-01-17 | 2025-02-24 |  |  | Threatened
USER REVIEW | NECESSARY STAKEHOLDERS | Not Started | 3 | 0.051724 | 0% | 0% | 2025-02-25 | 2025-02-25
SYSTEM INTEGRATION TESTING | QUALITY ASSURANCE | Not Started | 5 | 0.086207 | 0% | 0% | 2025-02-26 | 2025-03-14 |  |  | Overdue
Vulnerability Assessment | ITRISK | Not Started |  |  | 0% | 0% | 2025-03-14 | 2025-03-21
UAT | NECESSARY STAKEHOLDERS | Not Started | 5 | 0.086207 | 0% | 0% | 2025-03-24 | 2025-03-24
UAT SIGN-OFF | NECESSARY STAKEHOLDERS | Not Started | 1 | 0.017241 | 0% | 0% | 2025-03-25 | 2025-04-04
Database Access Request | NECESSARY STAKEHOLDERS | Not Started | 5 | 0.086207 | 0% | 0% | 2025-03-25 | 2025-04-04
Change Control Board Approval | NECESSARY STAKEHOLDERS | Not Started | 5 | 0.086207 | 0% | 0% | 2025-04-09 | 2025-04-09
DEPLOYMENT (Pilot) | DEVELOPER | Not Started | 53 |  | 0% | 0% | 2025-04-10 | 2025-04-11
Go-live Approvals | PROJECT MANAGER | Not Started |  |  | 0% | 0% | 2025-04-11 | 2025-04-16
DEPLOYMENT (G0-live) | DEVELOPER | Not Started | 58 |  | 0% | 0% | 2025-04-17 | 2025-04-17
19.83%

## Sheet1
STATUS | Status | Responsibility
On Track | On Track | BUSINESS ANALYST
Completed | Completed | PROJECT MANAGER
Threatened | Threatened | DEVELOPER
Overdue | Overdue | NECESSARY STAKEHOLDERS
On Hold | Not Started | INFOSEC
| On Hold | ITRISK
CIO
CUSTOMER EXPERIENCE
BUSINESS
QUALITY ASSURANCE
CHANNEL MANAGERS
VENDOR

## Risk Register
Risk Register
Risk | Impact | Likelihood | Mitigation Plan
Employee resistance | High | Low | Involve the team from inception and provide necessary training and support
Data breaches during migration | High | Low | Secure encryption, Data protection in alignment with the organization’s policy, and backups
Integration problems involving legacy systems | Medium | Medium | Perform compatibility testing
Over-budget concerns | Medium | Low | Strict budget control